## Sheet1
Global Project Schedule
Firmware | Task | Owner | Time | Notes:
Printer
| Messaging | Aaron | 3d | Convert KPC CAN to USB Msgs
| Memory Organization | Aaron | 3d
| Sensors (A/D) | Aaron | 5d | A/D Auto and Manual modes
| Printhead MOC | Aaron / Hung | 5d | New Printhead
| Takeup Synch | Aaron | 5d | New Takeup
| Low Stock Sense | Aaron | 3d | New Sensor
| Teach Tables | Aaron | 4d
| Avery Cutter Integration | Aaron | 3d | New
| Integration with Backend | Aaron | 7d
| DotWear | Aaron | 3d
80mm Printhead
| PrintEngine Support | Aaron | 3d
| MOC | Aaron / Hung | 3d
| DotWear | Aaron | 3d
Weigher
| Messaging | Joseph | 3d | Convert KPC CAN to USB Msgs
| CAT3 Support | Joseph | 2d | Map to new serial flash
| Weigher A/D | Joseph | 3d | New A/D
| ValueMax | Joseph | 6d | New Accelerometer
USB
| Enumeration | Aaron | 2d
| Integration | Aaron | 3d
| Unit Testing | Aaron | 3d
Bootloader
| Stand Alone project | Joseph | 1d
| Port KPC Bootloader | Joseph | 3d
| USB Enumeration | Joseph | 1d | Copy what was done in application
| Messaging | Joseph | 1d
| Integration | Joseph | 2d
| Unit Testing | Joseph | 2d
Backend
Upgrade MGR Daemon |  |  |  | Do this first and implement all USB messaging and unit test all messaging
| Finish design | Joseph / Aaron | 5d | Use what I have started which enumerated boot device
| Messaging | Joseph / Aaron | 7d | All messages
| Integration | Joseph | 2d
| Unit Testing | Joseph / Aaron | 5d / 2d | Joseph tests bootloader / Weigher messages. Aaron tests all other application messages
PrinterManager
| Messaging | Aaron | 5d
| Support Global Printer | Aaron | 5d
| Support Service Pages | Aaron | 5d
WeigherManager
| Comm Mgr | Joseph | 7d | (Use APC Comm MGR as reference )
| Messaging | Joseph | 2d
| CAT3 support | Joseph | 3d
| Value Max | Joseph | 4d
Backend Unit Tests
Printer | Messaging | Aaron | 2d
| Label Sizing | Aaron | 4d
| Vert, Horz, Expel | Aaron | 2d
| Manual mode print | Aaron | 1d
| Auto mode print | Aaron | 1d
| Virtual print | Aaron | 2d
| Production Entry | Aaron | 2d
| Linerless | Aaron | 2d
| Diecut | Aaron | 2d
| Service Pages | Aaron | 2d
Weigher | Messaging | Joseph | 2d
| CAT3 | Joseph | 2d
| ValueMax | Joseph | 2d
| Service Pages | Joseph | 2d